## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
1 | Title Page | 0.5 | Day 10: 0.5 | Alex | 6.5
2 | Table of Contents | 0.5 | Day 10: 0.5 | Liam | 6.5
3 | Section 1 Executive Summary with Narrative and Conclusions | 0.5 | [14 empty] | Karrington | 6.5 | bar: Day 13
4 | Company Background & Current Environment | 0.5 | [14 empty] | Sabrina | 6 | bar: Day 13
5 | Problem Analysis (BPA, BPI, BPR) | 1 | Day 12: 1; Day 13: 0.5 |  | 25.5 | Total Team Time
6 | Proposed System Objectives and Constraints | 1 | Day 12: 1; Day 13: 0.5
7 | Expected Benefits | 1 | Day 13: 2
8 | Team Charter | 0.5 | Day 13: 0.5
9 | Context Diagram | 2 | Day 12: 1.5
10 | Use Case Diagram | 1 | Day 12: 1; Day 13: 0.5
11 | Met with client | 1 | Day 9: 1; Day 13: 0.5
12 | Met with group | 10 | Day 9: 2; Day 11: 2; Day 12: 4; Day 13: 2
13 | Presentation | 2 | Day 12: 0.5; Day 13: 2
Remaining Effort |  | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 18.5 | 17.5 | 15.5 | 6.5 | -4 | -4
Ideal Effort |  | 21.5 | 19.9643 | 18.4286 | 16.8929 | 15.3571 | 13.8214 | 12.2857 | 10.75 | 9.2143 | 7.6786 | 6.1429 | 4.6071 | 3.0714 | 1.5357 | 0

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alex
Liam
Karrington
Sabrina
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alex
Liam
Karrington
Sabrina
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alex
Liam
Karrington
Sabrina
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alex
Liam
Karrington
Sabrina
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alex
Liam
Karrington
Sabrina
[18 empty] | 0 | Total Team Time
Total Project Time
[18 empty] | Sprint 1 | 25.5
[18 empty] | Sprint 2 | 0
[18 empty] | Sprint 3 | 0
[18 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | 0
[18 empty] | Sprint 6 | 0
[19 empty] | 25.5 | Total Project Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0