## Project Plan
Project Plan
| PROJECT: |  | Yaba Information System
| CO-Product Owner: |  | Liam Alexander
[5 empty] | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16
Task name | Start date | End date | Assigned | Progress | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
Sprint 1 | 2022-01-31 | 2022-02-10 |  | 100%
Title Page | 2022-02-05 | 2022-02-10 | Karrington | 100%
Table of Contents | 2022-02-05 | 2022-02-10 | Karrington | 100%
Section 1 Executive Summary with Narrative and Conclusions | 2022-02-07 | 2022-02-10 | Liam | 100%
Company Background & Current Environment | 2022-02-07 | 2022-02-10 | Liam | 100%
Problem Analysis (BPA, BPI, BPR) | 2022-02-07 | 2022-02-10 | Karrington | 100%
Proposed System Objectives and Constraints | 2022-02-07 | 2022-02-10 | Sabrina | 100%
Expected Benefits | 2022-02-07 | 2022-02-10 | Sabrina | 100%
Context Diagram | 2022-02-08 | 2022-02-10 | Alex | 100%
Sprint2 | 2022-02-10 | 2022-02-23
Section 2 Executive Summary with Narrative and Conclusions | 2022-02-11 | 2022-02-23
Use Case Diagram | 2022-02-12 | 2022-02-23 | Alex | 100%
Supplement Specifications (Non-Functional) | 2022-02-13 | 2022-02-23
Sprint 3 | 2022-02-23 | 2022-03-17
Section 3 Executive Summary with Narrative and Conclusions | 2022-02-24 | 2022-03-17
Complete Data Flow Diagram Package | 2022-02-25 | 2022-03-17
Hardware and Software Specification | 2022-02-26 | 2022-03-17
Navigation Diagram | 2022-02-27 | 2022-03-17
Entity Relationship Diagrams | 2022-02-28 | 2022-03-17
Program Plan showing logic and I/Os (IPO Chart with each program listed) | 2022-03-01 | 2022-03-17
Standard Naming Conventions | 2022-03-02 | 2022-03-17
Sprint 4 | 2022-03-17 | 2022-03-31
Section 4 Executive Summary with Narrative and Conclusions | 2022-03-18 | 2022-03-31
Test Plans | 2022-03-19 | 2022-03-31
Training Manual and/or Reference/Procedure Manual | 2022-03-20 | 2022-03-31
Technical Manual | 2022-03-21 | 2022-03-31
Sprint 5 | 2022-04-01 | 2022-04-14
Section 5 Executive Summary with Narrative and Conclusions | 2022-04-02 | 2022-04-14
Migration Plan (Business, Technical, People Readiness) | 2022-04-03 | 2022-04-14
Personal Project Assessment (by each member) | 2022-04-04 | 2022-04-14
Explanation of challenges, problems and discoveries | 2022-04-05 | 2022-04-14
All Burndown Charts, All Backlogs, All Meeting Logs | 2022-04-06 | 2022-04-14
Any other supporting documentation | 2022-04-07 | 2022-04-14

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com